## Sheet1
RESEARCH ADMINISTRATION PROCESS:
General Roles and Responsibilities
The following table/matrix aims to assist faculty, staff and other researchers on which research office will provide services for specific tasks.
Note that this is just a quick summary sheet. Each proposal/project may identify specific roles on a case-to-case basis.
DESCRIPTION OF CONTRACT, PROJECT, PURPOSE or ACTIVITY | PI | ORD (RGS) | AVP of RSP | OGC (Officer) | OSP Admin. | CO | OSP Compliance
Identification of Funding Opportunities
Meet with Faculty to identify faculty research interests and introduce them to campus resources (ex. Pivot RP, intramural funding, etc.) | X | X
Seek funding opportunities for proposals | X | X
Distribute funding opportunity information |  | X
Announce Limited Submission Opportunity to campus and run competition |  |  | X
Coordinate college internal review process for limited submission |  | X
Pre-submission requirements/CAYUSE Approvals
Inform ORD/OGC via email of Intent to Submit to a selected funding opportunity and sponsor deadline and collaborators/partners | X
If the deadline falls outside the timeline policy, secure AVP ORSP approval to initiate Cayuse routing | X
Determine PI eligibility to submit |  | X
Determine Institution eligibility and contact sponsor for clarification (as applicable). If sponsor is private, coordinate communication to sponsor with University Advancement and secure clearance to move forward with submission. |  | X
Determine submission methods (online, paper, email) and confirm university or PI access as applicable (e.g. Research.gov, Grants.gov, on-line submission system) |  |  |  | X
Meet with PI to review readiness and funding opportunity fit |  | X
Identify and discuss institutional requirements (limited submission, cost share, letters from campus leadership, space, partnerships, MOU, etc.) | X | X
Identify and discuss college resources and secure the necessary approvals (e.g. course release, institutional match/cost share, space, facilities/equipment, construction, etc.) | X | X
Identify subcontractors, consultants, and collaborators/partners in accordance with CSUF's timeline submission policy | X
Provide subcontractor contact information for each subcontractor project (PI/ORSP Contact) | X
Request and secure subcontractor budget, scope of work and relevant proposal documents, if applicable | X |  |  | X
Draft a project summary/project abstract/concept paper and provide to ORD | X
Complete Internal Routing Form to provide details regarding project personnel, certifications, protocol, and risk management items | X
Review Internal Routing Form for accuracy and completeness |  | X
Review routing documents and determine the appropriate and necessary compliance forms need (e.g. Financial Conflict of Interest form, Off-campus rate determination , PI eligibility, etc.) |  |  |  | X
Meet w/RGS and OGC Officer to discuss workplan, strategy and review timeline | X | X |  | X
Develop proposal checklist to identify target deadline for individual components of the application to meet sponsor deadlines. |  |  |  | X
Budget Development
Develop budget alongside draft statement of work/narrative, and prepare internal budget form | X |  |  | X
Draft Budget Narrative and Justification | X |  |  | X
Review and finalize proposal budget | X |  |  | X
Cayuse Routing
Initiate Cayuse Routing to secure necessary internal approvals (required documents: Solicitation/Guidelines/Program Announcement Routing Form, Internal Budget, Budget Narrative and draft Statement of Work/Narrative/Abstract) |  |  |  | X
Complete compliance forms as required by sponsor (Assurances and Certifications) |  |  |  | X
Proposal Preparation
Reach out to Program Contact/Officer for guidance and feedback on programmatic questions | X
Prepare proposal documents in accordance with sponsor guidelines/instructions | X
Edit and review proposal documents provided by PI before submission to OGC |  | X
Secure letters of support/commitment (ex. Collaborators, Community Partners & Congressperson, AVP-ORSP, Provost & President), if applicable | X | X
Complete application forms/institutional information in accordance with sponsor guidelines/instructions (ex. Research.gov, Grants.gov etc.) |  |  |  | X
Collect and review subrecipient documents, if applicable | X |  |  | X
Share and request feedback from colleagues and collaborators | X
Proposal Review and Approval
Send final proposal documents to OGC/ORD for final review | X
Review proposal packet for completeness and accuracy before submission |  | X |  | X
Follow up on internal Cayuse approvals to secure all the required approvals have been obtained prior to submission |  |  |  | X
Proposal Submission
For paper submissions: Send proposal to sponsors after institutional approvals have been secured |  |  |  | X
For electronic submissions (web or email): Submit proposal to sponsors after institutional approval |  |  |  | X
Provide cover letter identifying exceptional terms/conditions identified in funding opportunity/solicitation (as applicable) |  |  |  | X
Send a submission confirmation to PI/RGS along with a copy of the final submitted application. |  |  |  | X
Verify application has been received by the sponsor, if applicable |  |  |  | X
Other Pre-Award Activities
Follow up with sponsor regarding status of proposal, if applicable | X |  |  | X
Prepare Just-in-Time documents or other pre-award documents | X |  |  | X
Review, approve and submit Just in Time documents to sponsor |  |  |  | X
Request pre-award or advance funding account | X
Approve pre-award or advance funding request |  |  |  |  | X
Confirm status of award, firm commitment and/or allowability of pre-award spending with sponsor |  |  |  | X | X
Request an Organizational Prior Approval Spend (OPAS) | X |  |  |  | X
Review and approve OPAS |  |  |  |  | X
Monitor pre-award or advance funding account |  |  |  |  | X
Prepare, finalize and approve Small Business Subcontracting Plan (applicable for any single contract >$550,000) |  |  |  |  | X
Award Review and Acceptance
Send congratulations email to PI upon receipt of award notification |  |  |  | X
Review terms and conditions of award/agreement related to the technical and financial components of the project |  |  |  | X
Negotiate terms and conditions with sponsor - in consultation with PI and other appropriate office(s) |  |  |  | X
Accept or reject exceptional terms and conditions (in consultation with PI, OSP, appropriate campus units as applicable) |  |  |  | X
Confirm acceptance of exceptional terms and conditions |  |  |  | X | X
Approve award terms and conditions and, if applicable, execute award/agreement |  |  |  |  | X
Collect 700-U forms prior to acceptance of agreement from non-exempt foundations and private sponsor |  |  |  | X
Notify CSUF-HR regarding ethics training for 700-U form filers |  |  |  | X
Follow up on COI/ethics training |  |  | X
IRB or IACUC approval (as applicable) for new awards/renewals |  |  | X
Award Set-Up
Confirm that regulatory compliance approvals are in place (post-award) | [6 empty] | X
Request revised/updated budget(s) if needed |  |  |  |  | X
Assign account number and establish account in ASC system |  |  |  |  | X
Input budget in to ASC system |  |  |  |  | X
Prepare award summary documents (NOA) |  |  |  |  | X
Conduct Faculty Orientation for Post Award |  |  |  |  | X
Conducting the Project - Financial
Prepare financial transactions (i.e. cost transfers, payroll, requisitions, etc.) |  |  |  |  | X
Initiate purchases |  |  |  |  | X
Execute high-value purchases (>$4,500) |  |  |  |  | X
Review and approve financial transactions |  |  |  |  | X
Monitor and oversee financial expenditures |  |  |  |  | X
Initiate re-budgeting requests |  |  |  |  | X
Approve re-budgeting requests (if sponsor's prior approval not required) |  |  |  |  | X
Submit re-budgeting requests to sponsor for approval, if required by terms/conditions of the award/agreement |  |  |  |  | X
Initiate no cost extensions |  |  |  |  | X
Approve no cost extensions (or forward to sponsor for approval) |  |  |  |  | X
Certify that cost sharing is documented |  |  |  |  | X
Reconcile accounts on a monthly basis |  |  |  |  | X
Review Reconciled Accounts |  |  |  |  | X
Invoicing and Financial Reporting
Prepare and submit the invoice or financial report |  |  |  |  | X
Receive and deposit payments from sponsors |  |  |  |  | X
Produce and record a letter of credit draw request (federal awards) |  |  |  |  | X
Personnel and Effort Certification
Initiate hiring and appointment process |  |  |  |  | X
Maintain the effort certification database and reporting system | [6 empty] | X
Complete necessary adjustments to award changes and/or payroll distribution |  |  |  |  | X
Prepare effort reports and distribute | [6 empty] | X
Ensure effort reports are returned timely and follow-up | [6 empty] | X
Resolve problems or follow up on certifications not submitted | [6 empty] | X
Data and Intellectual Property Management
Review and approve incoming Material Transfer Agreements |  |  |  | X
Complete invention disclosure form | [6 empty] | X
Prior Approvals (e.g. Rebudgeting, PI Absence or Change, Foreign Travel, etc.)
Initiate prior approvals for changes to project |  |  |  |  | X
Review terms and conditions of award to determine if prior approvals are needed |  |  |  |  | X
Provide guidance on terms and conditions |  |  |  |  | X
Initiate prior agency approval process |  |  |  |  | X
Forward prior approval requests to the sponsor, when sponsor approval is required |  |  |  |  | X
Obtain sponsor's decision regarding change(s) to the project and update ASC systems as necessary |  |  |  |  | X
Subcontracts and Subawards
Prepare/complete subcontractror Risk Assessment Analysis | [6 empty] | X
Upon receipt of a Prime Award, initiate Subaward Issurance Form for new subawards and send to PI |  |  |  | X
Upon receipt of Subaward Issuance Form, draft Subcontract |  |  |  | X
Request/initiate Subaward/Subcontract Issuance Form for amendments to existing subawards/subcontracts. |  |  |  |  | X
Prepare, negotiate, and sign subcontracts/subawards and subsequent modifications |  |  |  | X | X
Oversee programmatic aspects of subcontract/subaward | X |  |  |  | X
Review and approve subcontract invoices and send to Accounts Payable |  |  |  |  | X
Pay subcontract invoices approved by PI/Department |  |  |  |  | X
Project End and Closeout
Identify early closeout situations (e.g. project completion, early termination, etc.) |  |  |  |  | X
Ensure all appropriate expidentures have been posted to accounts |  |  |  |  | X
Prepare final financial invoice/report |  |  |  |  | X
Resolve issues related to unreconciled accounts |  |  |  |  | X
Submit and maintain financial reports to sponsor |  |  |  |  | X
Submit technical reports to sponsor | X
In the absence of the PI (e.g. transfer, long-term absence, etc.) prepare and submit technical reports to sponsor |  |  |  |  | X
Maintain reports for sponsored projects |  |  |  |  | X
Submit and maintain final invention reports to sponsor |  |  |  |  | X
Inactivate award account(s) in financial accounting system |  |  |  |  | X
Audits
Coordinate external audits for ASC |  |  |  |  | X
Coordinate A-133 audit |  |  |  |  | X